ZOIKO LOCAL
Phase 1 Engineering Build Roadmap
Final Locked Version

| Field | Detail |
| --- | --- |
| Document type | Engineering Build Roadmap - decision-grade execution plan |
| Audience | Founder & Executive Chairman, Global CTO, Engineering Leads, Product, QA, Security, Compliance, ZoikoNex Team |
| Status | Final locked - incorporates Founder decisions |
| Date | 29 May 2026 |
| Strategic role | Skype successor for cross-border life and business: local numbers, reliable calling, video, AI receptionist, compliance, billing, auditability |

# 0. Founder Decisions Now Locked

This version supersedes the prior roadmap. The following decisions are now locked into the build plan and must not be re-opened without Founder and CTO approval.

| Decision | Locked position | Engineering consequence |
| --- | --- | --- |
| Audience | Business and individual customers launch in Phase 1. | One platform, two configured surfaces: business workspace and individual account. No separate codebases. |
| Video | Video calling launches in Phase 1. | WebRTC/video provider integration, TURN/STUN, consent-aware recording hooks and video event metering are Phase 1 workstreams. |
| AI Receptionist | AI Receptionist launches in Phase 1. | AI receptionist is not Phase 2. It ships with guarded capabilities, business-hours logic, consent, escalation and human handoff. |
| Launch markets | USA, UK, Canada, plus selected business-friendly and high-demand corridors including Nigeria, South Africa, Ghana, Kenya, Mexico and additional approved markets. | Compliance, numbering, KYC/KYB and provider availability are planned as a controlled multi-market Phase 1 launch, not a three-country MVP. |

# 1. Executive Doctrine

Zoiko Local Phase 1 is a production-grade, AI-native, video-capable, business-and-consumer communications platform. It is not a narrow second-number app and it is not a lightweight Skype clone. It must launch with the core capabilities required to be credible as the successor to Skype for cross-border customers: local numbers, reliable calling, video calling, intelligent voicemail, AI receptionist, business accounts, individual accounts, ZoikoNex billing, compliance controls, and full auditability.

- Build the core as a platform, not an app. Numbering, voice, video, AI, billing and compliance are separate planes with clean interfaces.

- Serve businesses and individuals from one architecture. Individual users are single-seat accounts; businesses are multi-seat workspaces. This prevents future product drift.

- Buy infrastructure, build differentiation. CPaaS, video, transcription, LLM and KYC can be bought. Number lifecycle, customer experience, entitlements, compliance rules and evidence must be Zoiko-owned.

- Abstract early, switch later. Provider Gateway is mandatory from Day 1, even where Phase 1 uses one primary provider per capability.

- No silent failure. Every failed number purchase, provisioning event, billing sync, AI action and admin intervention must create an event, an audit record and a recovery path.

# 2. Phase 1 Scope - Locked

| Capability area | Phase 1 locked scope |
| --- | --- |
| Accounts | Individual accounts and business workspaces. Business roles: Owner, Admin, Member. Viewer/Auditor can be Phase 1.5 unless required by enterprise pilot. |
| Numbers | Search, reserve, purchase, activate, suspend, cancel and quarantine local numbers across approved Phase 1 markets. |
| Voice | Inbound calling, outbound calling, call forwarding, voicemail, call logs, business-hours routing and usage metering. |
| Video | 1:1 and small-group video calling through a specialist WebRTC provider; screen sharing where provider-supported; event metering from launch. |
| AI voicemail intelligence | Voicemail transcription, summary, language detection, suggested follow-up and searchable voicemail history where consent and law permit. |
| AI Receptionist | Business-hours answering, caller qualification, message capture, summary, urgency detection, routing/escalation to humans and audit trail. |
| Subscriptions | Plan tiers, trial logic, entitlements, usage allowances, overage capture and ZoikoNex billing integration. |
| Compliance | Country rules, KYC/KYB, consent records, AI processing gates, recording/transcription rules, emergency disclosures and audit evidence. |
| Admin operations | Operations console with RBAC, customer/number search, provisioning recovery, compliance case view, provider status and audit log viewer. |
| Customer surfaces | Web dashboard, iOS app and Android app. Mobile calling experience cannot be deferred. |
| Notifications | Email, SMS, push and in-app notifications for activation, voicemail, missed calls, receptionist summaries, billing and service events. |

# 3. Phase 1 Launch Market Doctrine

The launch-country strategy must balance business demand, diaspora relevance, numbering availability, regulatory clarity, KYC/KYB burden, provider coverage and support readiness. Phase 1 is therefore a controlled multi-market launch, not a token MVP. The CTO may sequence markets inside Phase 1, but the product architecture must be capable of supporting the full approved set.

| Market tier | Markets | Purpose | Launch condition |
| --- | --- | --- | --- |
| Tier A - anchor markets | USA, UK, Canada | High business demand, strong cross-border calling relevance, premium customer acquisition and business credibility. | Must be supported at public launch unless provider or regulatory blockers are unresolved. |
| Tier B - high-value growth corridors | Nigeria, South Africa, Ghana, Kenya, Mexico | Strong diaspora, SME, remittance, outsourcing, trade and cross-border family/business use cases. | Launch in Phase 1 where numbering/KYC/provider readiness is confirmed; otherwise launch in controlled Phase 1 wave within the same program. |
| Tier C - business-friendly expansion candidates | UAE, Singapore, Australia, Ireland, Netherlands | Business-friendly hubs with international company formation, remote teams, trade and investor networks. | CTO and Commercial Director approve based on provider coverage, compliance burden and launch economics. |

Market rule: no country goes live because it is attractive commercially unless four gates pass: numbering supply confirmed, compliance rules encoded, KYC/KYB path tested, and support runbook completed.

# 4. Delivery Model - Parallel Tracks

The build must not run as a sequential waterfall. Engineering runs in parallel tracks with monthly integration gates. The roadmap assumes Zoiko has a large technical team and can support aggressive parallel delivery without lowering quality.

| Track | Owner | Primary scope | Non-negotiable output |
| --- | --- | --- | --- |
| A - Platform & Provider Foundation | Backend Lead, DevOps/SRE, Telecom Lead | Cloud foundation, CI/CD, event bus, Provider Gateway, number inventory, provisioning orchestration. | Stable environments, provider interfaces, number lifecycle and recovery architecture. |
| B - Identity, Billing & Compliance | Backend Lead, Compliance Tech Lead, ZoikoNex Lead | Accounts, teams, subscriptions, entitlements, ZoikoNex events, compliance rules, consent and audit. | Account and billing truth connected to ZoikoNex with evidence-grade compliance controls. |
| C - Voice, Video & AI | Telecom Lead, Media Lead, AI Lead | Inbound/outbound voice, voicemail, video, transcription, AI voicemail intelligence, AI receptionist, semantic search. | Real communications experience with consented intelligence, not decorative AI. |
| D - Customer Experience & Admin | Product, Web Lead, Mobile Leads, Design Lead | Web, iOS, Android, admin console, onboarding, settings, notifications and support tools. | Customers and operations can complete the full journey without engineer intervention. |
| E - QA, Security & Launch Readiness | QA Lead, Security Lead, SRE, Compliance | Test automation, penetration testing, accessibility, load, failover, app-store readiness, runbooks. | Go/no-go evidence, not opinion. |

# 5. Nine-Month Execution Roadmap

The target is nine months to production-grade launch with a properly staffed team. The program can be accelerated only by adding verified delivery capacity; it cannot be accelerated by weakening compliance, auditability, billing reconciliation or number-reservation safety.

| Period | Execution focus | Exit gate |
| --- | --- | --- |
| Month 1 - Foundation lock | Lock countries, providers, hosting region, ZoikoNex contract, number state machine, entitlement model, compliance rule format, AI consent model, audit event standard. Stand up environments, CI/CD, observability, PostgreSQL, Redis, event bus, object storage, secrets, API gateway and feature flags. | All critical cross-track interfaces signed off. No unresolved provider, billing, compliance or data-model ambiguity. |
| Months 2 - Core platform | Provider Gateway v1, number inventory, atomic reservation, identity, business workspaces, individual accounts, compliance v1, billing adapter v1, inbound voice proof-of-life, admin console v1, web/mobile shells. | End-to-end demo: create account, search number, reserve, pass mock compliance, purchase via mock billing, activate and receive inbound call. |
| Months 3 - Commercial core | Real KYC/KYB, live ZoikoNex sync, subscription enforcement, outbound calling, voicemail, forwarding, usage metering, customer number purchase flow, mobile call handling and admin recovery queue. | Paid internal transaction: real number, real KYC/KYB, real ZoikoNex charge, real inbound and outbound call. |
| Months 4 - AI, video and receptionist | Video calling, TURN/STUN, transcription pipeline, AI voicemail intelligence, post-call summary, AI receptionist guarded launch, consent gates, conversation artifact model, semantic search and customer-facing AI controls. | Feature-complete launch candidate: business and individual journeys operate end-to-end across approved launch markets. |
| Months 5 - Hardening and launch | QA, load testing, reservation chaos tests, provider failover drills, billing reconciliation, security testing, accessibility, app store submission, compliance review, support training, incident runbooks and status page. | Founder + CTO + Compliance go/no-go. Any automatic No-Go trigger blocks launch. |

# 6. Number Lifecycle - Hard Engineering Spec

The number lifecycle is the heart of Zoiko Local. It must be safer than a normal ecommerce checkout because the purchased asset is a communications identity.

| State | Meaning | Required control |
| --- | --- | --- |
| Available | Number can be displayed and selected. | Provider availability checked and Zoiko inventory not assigned. |
| Reserved | Customer has a temporary hold. | Distributed lock with strict TTL, default 12 minutes, keyed on provider number identifier. |
| Purchase Pending | Checkout or ZoikoNex confirmation in progress. | No second customer can purchase. Payment failure returns number to controlled state, not instantly to public inventory. |
| Compliance Pending | KYC/KYB or country-rule requirements outstanding. | Customer communication, admin visibility and expiry timer. |
| Provisioning | Provider activation in progress. | Retry policy, idempotency key and reconciliation event. |
| Active | Customer owns and can use the number. | Billing, entitlements, routing and audit all aligned. |
| Suspended | Service temporarily limited. | Incoming-call grace policy and dunning/compliance reason captured. |
| Cancelled / Released | Customer no longer owns number. | Quarantine period before reuse, default 90 days. |

Atomicity law: two customers must never be able to reserve or purchase the same number. This must be verified by load and chaos testing before launch. Provider inventory is a source input; Zoiko inventory is the ownership truth.

# 7. AI Receptionist - Phase 1 Product and Architecture Standard

AI Receptionist is Phase 1, but it must launch as a governed receptionist, not as an uncontrolled conversational agent. The first version should be commercially useful, legally safer and operationally auditable.

| Component | Phase 1 requirement |
| --- | --- |
| Answering mode | Enabled per business number, with business-hours rules and explicit customer configuration. |
| Caller qualification | Capture caller name, company, reason for call, urgency and preferred callback channel. |
| Routing | Escalate to nominated team member, shared inbox or voicemail based on rules. |
| Human handoff | Transfer or notify when caller requests human help or urgency threshold is met. |
| Summary | Generate receptionist summary, transcript where legal, action item and suggested next step. |
| Guardrails | No legal, financial, medical or binding commercial commitments. No quoting prices unless customer-approved scripts exist. |
| Evidence | Store prompt version, transcript availability, consent basis, action taken, escalation path and customer notification. |

# 8. Video Calling - Phase 1 Standard

Video calling is Phase 1 because Skype replacement credibility requires it. The implementation should be deliberately narrow: useful enough for individuals and SMBs, not a Zoom-scale meeting platform.

- Phase 1 capacity: 1:1 and small-group video, target up to 8 participants.

- Architecture: buy specialist WebRTC/video infrastructure; own orchestration, permissions, entitlements, identity and metering.

- Network: TURN/STUN coverage across launch regions; failed NAT traversal is a launch blocker.

- Compliance: recording/transcription off by default and gated by jurisdiction, consent and retention policy.

- Billing: video participant-minutes metered for future pricing even if included in early plans.

# 9. Buy-vs-Build Decisions

| Layer | Decision | Phase 1 posture | Reason |
| --- | --- | --- | --- |
| Numbering & PSTN voice | Buy first | Telnyx, Twilio, Vonage or equivalent through Provider Gateway. Secondary providers added where launch-market risk requires. | Fastest safe route to market; margin can be reclaimed later through direct carrier relationships. |
| Video infrastructure | Buy | LiveKit Cloud, Daily.co, Vonage Video or equivalent. | WebRTC infrastructure is specialized; Zoiko differentiation is orchestration and product experience. |
| Transcription | Buy multi-vendor | Deepgram, AssemblyAI and/or self-hosted Whisper for sensitive workloads. | Language performance varies; multi-vendor prevents quality and cost lock-in. |
| LLM layer | Buy multi-vendor | OpenAI, Anthropic and self-hosted Llama/Mistral option behind AI Gateway. | AI vendor lock-in is unacceptable for a communications evidence product. |
| KYC/KYB | Buy | Sumsub, Onfido or equivalent. | Regulated infrastructure with document coverage and fraud networks. |
| Billing | Use ZoikoNex | Zoiko Local owns entitlements; ZoikoNex owns invoice, payment, dunning and reconciliation. | Avoid duplicating parent billing infrastructure. |
| Number lifecycle | Build | Zoiko-owned service. | Core product and trust asset. |
| Compliance rules | Build | Data-driven, versioned, audited rules engine. | Differentiator and regulatory safety layer. |
| Audit and evidence | Build | Immutable event and evidence service. | Trust foundation; cannot be outsourced as a thin log. |

# 10. Team and Staffing

The roadmap assumes Zoiko has a large technical team. The minimum recommended staffing below supports a nine-month Phase 1 with business and individual launch, video, AI Receptionist, multi-market compliance and ZoikoNex integration.

| Function | Recommended headcount | Reason |
| --- | --- | --- |
| Engineering Director / VP | 1 | Single accountable delivery leader. |
| Engineering Managers | 2 | Platform, media/AI and customer/admin tracks. |
| Backend Engineers | 4 | Identity, numbering, provisioning, billing, compliance, audit, entitlements and Provider Gateway. |
| Telecom / CPaaS Specialists | 2 | Numbering, SIP/PSTN, routing, CDRs, provider failover. |
| Real-Time Media / WebRTC Engineers | 2 | Video calling, TURN/STUN, meeting orchestration and media quality. |
| AI / ML Engineers | 2 | Transcription, AI voicemail, AI receptionist, semantic search, prompt/model governance. |
| Web Frontend Engineers | 3 | Dashboard, onboarding, billing, admin-visible customer flows. |
| iOS Engineers | 2 | Native calling, voicemail, video and push experience. |
| Android Engineers | 2 | Native calling, voicemail, video and push experience. |
| DevOps / SRE | 2 | Environments, observability, incident response, scaling and failover. |
| QA / Automation Engineers | 2 | Regression, mobile device testing, call-quality, billing and chaos tests. |
| Security Engineers | 2 | Appsec, threat modelling, pen-test remediation, secrets and access control. |
| Compliance / Legal-Tech Engineers | 2 | Rules engine, consent, KYC/KYB, audit evidence and market readiness. |
| Product Managers | 1 | Business, individual/mobile, platform/operations. |
| Product Designers | 1 | Business dashboard, consumer mobile, admin/operations. |
| Total | 30 | Appropriate for the locked Phase 1 ambition. Smaller teams require either longer timeline or narrower scope. |

Indicative Phase 1 budget envelope: with a 30 person blended global team, cloud/provider usage, compliance, audit, security and launch operations, the program should be planned as a material strategic build. The Founder and CTO should approve headcount and budget together; reducing one without reducing scope will create execution risk.

# 11. Go / No-Go Criteria

Launch is GO only when every critical criterion below is true. These criteria apply across business and individual journeys.

| Category | Launch requirement |
| --- | --- |
| Functional | Number purchase and activation works end-to-end in every approved launch market without engineer intervention. |
| Functional | Inbound and outbound calling complete reliably; voicemail captures, stores and plays back without loss. |
| Functional | Video calling works on web, iOS and Android across supported network conditions. |
| Functional | AI voicemail intelligence and AI Receptionist work only where consent and jurisdictional gates allow. |
| Billing | ZoikoNex subscriptions, payments, entitlements, dunning and usage events reconcile with zero unrecovered critical events. |
| Compliance | KYC/KYB, consent, transcription/recording rules, emergency disclosures and data retention are encoded per market. |
| Audit | Every admin action, compliance decision, AI processing event, billing state change and provisioning state change is auditable. |
| Quality | No P0 bugs open; p95 call setup under 3 seconds; p99 read API under 800ms; launch-week load tested at 10x expected traffic. |
| Security | Penetration test complete with no unresolved critical findings. Secrets, provider keys and privileged admin actions secured. |
| Operations | 24/7 on-call staffed, support trained, status page live, incident runbooks completed and failover drills executed. |

# 12. Automatic No-Go Triggers

- Two customers can reserve or purchase the same number under any test condition.

- Billing can succeed while provisioning fails without an automated recovery path and admin alert.

- AI processes call, voicemail or receptionist content without valid consent and legal basis.

- Any admin action occurs without immutable audit evidence.

- Any compliance rule is hardcoded in application logic rather than stored as versioned data.

- Voice, video, ZoikoNex billing, AI Receptionist or Provider Gateway has an undocumented single point of failure.

- Support cannot resolve the top 20 failure modes without engineering intervention.

# 13. Risk Register

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Scope pressure | Business + individual + video + AI Receptionist + multi-market launch is ambitious. | Protect Phase 1 scope through change-control. New features become Phase 1.5 unless Founder and CTO approve trade-off. |
| Provider dependency | CPaaS, video, transcription and LLM providers can fail, raise prices or restrict markets. | Provider Gateway, multi-vendor posture for critical layers and failover runbooks. |
| Regulatory complexity | Launch markets have different telecom, KYC, AI, recording and data rules. | Compliance engineer from Day 1; rules as data; market readiness gate before each country launch. |
| AI trust failure | Incorrect receptionist or voicemail summaries can damage business trust. | AI outputs labelled, editable, audited and constrained; golden-set testing; human handoff and no binding commitments. |
| Real-time quality | Voice and video failures are immediately visible and can destroy confidence. | Media-plane SLOs, monitoring, TURN/STUN coverage, call-quality telemetry and provider failover. |
| Billing/provisioning mismatch | Customers may pay but not receive numbers, or receive service without billing. | Event-driven reconciliation, idempotency, dunning policy and operational recovery queue. |

# 14. Final Doctrine

Zoiko Local Phase 1 must ship as a serious communications platform: local numbers, inbound and outbound calling, voicemail, video calling, AI voicemail intelligence, AI Receptionist, business workspaces, individual accounts, ZoikoNex billing, compliance controls, auditability and operational recovery. The goal is not to imitate Skype. The goal is to replace what Skype made familiar and surpass it with governed intelligence, business readiness, local-number credibility and a platform architecture that can scale into advanced communications.

The execution standard is clear: build the foundation first, abstract providers from Day 1, treat compliance as code, treat evidence as product, integrate ZoikoNex as the billing spine, make AI useful but governed, make video real but controlled, and do not launch any market that cannot be supported operationally.

Locked position: Phase 1 is wide because the ambition requires it and Zoiko has the technical capacity. It is still controlled because every launch market, provider, AI feature and communications path must pass hard readiness gates before going live.

# 15. Immediate CTO Action Items

| Action | Owner | Deadline |
| --- | --- | --- |
| Confirm Phase 1 market list and launch sequencing within Tier A, Tier B and Tier C. | Founder + CTO + Commercial Director | Before engineering kickoff |
| Shortlist CPaaS, video, transcription, LLM and KYC providers. | CTO + Telecom Lead + AI Lead | Week 1 |
| Lock ZoikoNex billing event contract and entitlement model. | CTO + ZoikoNex Lead + Finance Systems | Week 2 |
| Approve AI Receptionist Phase 1 guardrails and prohibited actions. | CTO + Product + Legal/Compliance | Week 2 |
| Approve staffing plan and named engineering owners by track. | Founder + CTO | Week 2 |
| Create market-readiness checklist for each launch country. | Compliance Lead + Product + Telecom Lead | Week 3 |